## Sheet1
TEAM 2 - BUSN3600 TERM PROJECT - SCHEDULE
Tasks | JULY | [30 empty] | AUGUST
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
| f | s | s | m | t | w | t | f | s | s | m | t | w | t | f | s | s | m | t | w | t | f | s | s | m | t | w | t | f | s | s | m | t | w
Agreement on scope, and divide the Project Charter content among the team members | bar: f
Write the project purpose and justification
Write the project objectives and related success criteria
Write the project description - high level project description
Write the summary milestone schedule
Write the major deliverables
Write the summary estimated budget
Write the risk and mitigation plan
Write the stakeholder list
Write the project approval requirements
Assign the project manager responsability, and authority level
Write the project charter acceptance
Integrate and review project charter | bar: t to t
Deliver project charter to project sponsor | bar: w
Work Plan
Divide the Work Plan content among the team members | bar: f
Write the scope statement
Write the work breakdown structure
Write the schedule
Write detailed stakeholder analysis
Write communication plan
Integrate and review work plan | bar: t to t
Deliver work plan to project sponsor | bar: w
Research Essay
Write the essay
Research, discuss and choose two successful and two failed business projects | bar: t to s
Brainstorming | bar: m
Map out the structure of the argument | bar: t
Divide essay paragraphs among the team members | bar: t
Write the introduction | bar: w to s
Write the body paragraphs | bar: w to s
Write the conclusion | bar: w to s
Integrate and review - complete draft | bar: m to f
Review draft - complete final essay | bar: s to t
Submitt final essay to Turnitin | bar: w
Team Video Presentation
Define script | bar: s to t
Define better tool to video production | bar: t to w
Define video style | bar: t to w
Record audios | bar: w to t
Integrate audios and images - complete draft | bar: t to s
Review draft - complete final video version | bar: m to t
Upload video to Blackboard | bar: w